## Product Backlog
Product Backlog
Backlog ID | User Story
101 | As a Student I Want………………..
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120

## Sprint Backlogs
Sprint 01 |  |  | Sprint 01 |  |  | Sprint 01 |  |  | Sprint 01 |  |  | Sprint 01
Product Backlog ID | Sprint Backlog ID | User Story | Product Backlog ID | Sprint Backlog ID | User Story | Product Backlog ID | Sprint Backlog ID | User Story | Product Backlog ID | Sprint Backlog ID | User Story | Product Backlog ID | Sprint Backlog ID | User Story
101 | 1001 | Data Collection | 101
| 1002 | Feature Selection
| 1003 | Feature Engineering
| 1004 | Data Encodeing

## Sprint_01 BurnDown Chart
SPRINT 1 BURNDOWN CHART
Backlog_ID | User Stories/Sprint Backlog | Initial Estimate | 2010-07-01 | 2011-07-01 | 2012-07-01 | 2013-07-01 | 2014-07-01 | 2015-07-01 | 2016-07-01 | 2017-07-01 | 2018-07-01 | 2019-07-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1004 | Problem Definition | 4 | 2010-07-01: 1; 2011-07-01: 2; 2012-07-01: 1
1005 | Literature Research | 3 | 2014-07-01: 1; 2015-07-01: 2
1006 | Project Planning | 3 | bar: 2016-07-01 to 2018-07-01
Remaining Effort |  | 10 | 9 | 7 | 6 | 6 | 5 | 3 | 2 | 1 | 0 | 0
Ideal Trend |  | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0

## Sprint_02 BurnDown Chart
SPRINT 2 BURNDOWN CHART
Backlog_ID | User Stories/Sprint Backlog | Initial Estimate | 2025-07-01 | 2026-07-01 | 2027-07-01 | 2028-07-01 | 2029-07-01 | 2030-07-01 | 2001-08-01 | 2002-08-01 | 2003-08-01 | 2004-08-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1004 | Data Collection | Day 0: 8; Day 1: 3; Day 2: 2; Day 3: 2; Day 4: 1
1005 | Feature Selection | Day 0: 5; Day 4: 2; Day 5: 2; Day 6: 1
1006 | Feature Engineering | Day 0: 4; Day 6: 1; Day 7: 2; Day 8: 1
1007 | Data Encoding | Day 0: 3; Day 9: 2; Day 10: 1
Remaining Effort |  | 20 | 17 | 15 | 13 | 10 | 8 | 6 | 4 | 3 | 1 | 0
Ideal Trend |  | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0